## Summary
FW Gatekeeper Feature Tracker
Canonical user-story tracker generated 2026-06-21T19:34:54.140Z. Source: current code in /Users/noahthies/Documents/GitHub/fw-gatekeeper
Metric | Value | Status Legend | Meaning
User stories tracked | 34 | Ready for validation | Feature is mapped from code and waiting for focused validation.
Stories with passing test evidence | 34 | Tested pass | A command/browser check has passing evidence.
Stories with documented errors | 0 | Error documented | A reproducible failure is logged in Test Log.
Stories fixed or retested | 20 | Fixed; needs retest | A code fix was applied and awaits the same test.
Stories blocked | 0 | Retest passed | The post-fix test passed.
|  | Blocked | Validation needs missing external service, credentials, camera, or hardware.

## User Stories
Story ID | Area | Feature | User Story | Expected Behavior | Code Source | Verification Surface | Feature Status | Priority | Test Status | Error / Notes | Fix Status | Retest Status
AUTH-001 | Authentication | Login | As a portal user, I can sign in with a named account or the legacy admin PIN so that authorized staff can reach the command center. | Email/password submit calls Convex Auth password sign-in and shows normalized errors; legacy PIN submit posts to /api/auth/login, sets the fw-auth cookie on success, and redirects to /. | src/app/login/page.tsx; src/app/api/auth/login/route.ts; convex/auth.ts | test:auth-scaffold; test:login-error-copy | Tested pass | High | Pass / Blocked | PIN login returned fw-auth cookie; authenticated GET /briefing and /closeout returned 200 with expected SSR text; /exceptions returned 200 with Shift Exceptions heading; / returned 200 with Dashboard shell. ¦ In-app Browser rendered /login but repeated locator interaction flipped the dev page into a Next overlay: TypeError Cannot read properties of undefined reading call. Standalone Playwright did not reproduce the login failure. | Not needed yet
AUTH-002 | Authentication | Logout | As a signed-in user, I can sign out so that browser access is cleared. | Sidebar logout clears the legacy auth cookie and calls Convex signOut; failures stay visible instead of silently redirecting. | src/components/Sidebar.tsx; src/app/api/auth/logout/route.ts | test:auth-scaffold | Retest passed | High | Retest Pass | Convex Auth scaffold contract passed after the Convex client lazy-init fix. | Not needed yet
AUTH-003 | Authorization | Role Gates | As an admin, enrollment user, or viewer, I only see and call features my role is allowed to use. | Middleware protects non-public pages, allows kiosk-key endpoints, restricts admin-only pages, and lets selected read APIs support viewer/enrollment roles. | src/middleware.ts; src/lib/portal-auth.ts; src/lib/portal-member.ts | test:auth-scaffold; test:enrollment-permissions; test:kiosk-readiness | Tested pass | High | Pass | Kiosk readiness contract passed. | Not needed yet
NAV-001 | Navigation | Responsive Shell | As a mobile or desktop user, I can navigate the command center without losing access to primary actions. | Desktop sidebar shows permitted routes; mobile header/bottom navigation keeps dashboard, workers, enroll, and a more menu reachable without covering content. | src/components/AppShell.tsx; src/components/Sidebar.tsx | test:worker-ui; test:kiosk-readiness | Retest passed | Medium | Retest Pass / Pass | Worker UI and dashboard readiness contract passed after the Convex client lazy-init fix. ¦ Standalone Playwright fallback: PIN fallback enabled after input and navigated to dashboard with Action Center visible. | Not needed yet
DASH-001 | Dashboard | Today Overview | As a supervisor, I can see today's attendance state at a glance. | Dashboard polls stats, workers, attendance, system health, exceptions, and closeout data; it shows worker totals, clocked-in/out/not-arrived counts, roster cards, search, and last updated time. | src/app/page.tsx; src/components/StatsBar.tsx; src/components/WorkerCard.tsx | test:worker-ui | Retest passed | High | Pass / Pass | PIN login returned fw-auth cookie; authenticated GET /briefing and /closeout returned 200 with expected SSR text; /exceptions returned 200 with Shift Exceptions heading; / returned 200 with Dashboard shell. ¦ Standalone Playwright fallback: PIN fallback enabled after input and navigated to dashboard with Action Center visible. ¦ Production build failed when API route imports constructed ConvexHttpClient during Next page-data collection without NEXT_PUBLIC_CONVEX_URL. | Retest Pass | npm run build passed; selected contracts and Python compile passed after fix.
DASH-002 | Dashboard | Action Center | As a supervisor, I can see the next operational actions before trusting the shift. | Missing/invalid face data, kiosk warnings, schedule warnings, open exceptions, absent workers, and closeout status appear as action cards with clear CTAs; all-clear state is explicit. | src/app/page.tsx | test:worker-ui; test:shift-exceptions; test:shift-closeout | Retest passed | High | Retest Pass / Pass | Production build completed after making src/lib/convex.ts lazy initialize ConvexHttpClient. ¦ Standalone Playwright fallback: PIN fallback enabled after input and navigated to dashboard with Action Center visible. ¦ Production build failed when API route imports constructed ConvexHttpClient during Next page-data collection without NEXT_PUBLIC_CONVEX_URL. | Retest Pass | npm run build passed; selected contracts and Python compile passed after fix.
DASH-003 | Dashboard | Recent Signals | As a supervisor, I can distinguish attendance events from system warnings in the recent timeline. | Recent timeline contains source markers for attendance and system-warning events and links users to the relevant review surface. | src/app/page.tsx | test:worker-ui | Retest passed | Medium | Retest Pass | Worker UI and dashboard readiness contract passed after the Convex client lazy-init fix. | Not needed yet
WORK-001 | Workers | Worker Readiness List | As an admin, I can see which workers are ready for kiosk recognition. | Workers page lists people as cards, shows employee ID, department, face-enrolled/missing/invalid status, and offers edit, deactivate, enroll, or re-enroll actions. | src/app/workers/page.tsx; src/app/api/workers/route.ts; convex/workers.ts | test:worker-ui | Retest passed | High | Retest Pass / Pass | Worker UI and dashboard readiness contract passed after the Convex client lazy-init fix. ¦ Standalone Playwright fallback found Workers and no Next overlay. | Not needed yet
WORK-002 | Workers | Worker Maintenance | As an admin, I can update worker metadata or deactivate a worker without exposing biometric vectors unnecessarily. | PATCH updates name, employee ID, department, or face encoding when authorized; DELETE removes/deactivates; list only includes raw face vectors when include_encodings=true. | src/app/workers/page.tsx; src/app/api/workers/route.ts; convex/workers.ts | test:worker-ui; test:enrollment-permissions | Tested pass | High | Pass / Pass | Enrollment permission contract passed. ¦ Standalone Playwright fallback found Workers and no Next overlay. | Not needed yet
ENROLL-001 | Enrollment | New Face Enrollment | As an enrollment user, I can create a worker with usable face data. | Enrollment collects name, employee ID, department, captures three webcam photos, sends them to the face encoder, uploads photos, stores a valid encoding, and fails honestly when no usable face vector exists. | src/app/enroll/page.tsx; src/app/api/enroll/route.ts; src/components/WebcamCapture.tsx; src/lib/encoding.ts | test:worker-ui; test:enrollment-permissions | Tested pass | High | Pass / Pass | Enrollment permission contract passed. ¦ Standalone Playwright fallback found Enroll and no Next overlay. | Not needed yet
ENROLL-002 | Enrollment | Re-enrollment | As an enrollment user, I can update an existing worker's face data without accidentally changing restricted metadata. | Enroll page reads worker_id, pre-fills existing metadata, submits workerId, and preserves metadata for enrollment-role sessions unless admin permissions allow changes. | src/app/enroll/page.tsx; src/app/api/enroll/route.ts | test:worker-ui; test:enrollment-permissions | Tested pass | High | Pass / Pass | Enrollment permission contract passed. ¦ Standalone Playwright fallback found Enroll and no Next overlay. | Not needed yet
ONBOARD-001 | Onboarding | Enrollment Guide | As an implementer or supervisor, I can follow plain instructions for enrolling workers correctly. | Onboarding guide links to enrollment, explains step-by-step capture, kiosk camera best practice, pre-flight checks, common mistakes, troubleshooting, and email copy. | src/app/onboarding/page.tsx | Browser smoke | Tested pass | Medium | Pass | Standalone Playwright fallback found Step-by-step enrollment and no Next overlay. | Not needed yet
LOG-001 | Activity | Activity Log | As a supervisor, I can review clock events and audited corrections for a day. | Activity Log fetches attendance and attendance corrections by date, shows correction history, and exports the visible activity as CSV. | src/app/log/page.tsx; src/app/api/attendance/route.ts; src/app/api/attendance-corrections/route.ts | test:attendance-corrections | Retest passed | High | Retest Pass / Pass | Production build completed after making src/lib/convex.ts lazy initialize ConvexHttpClient. ¦ Standalone Playwright fallback found Correction history and no Next overlay. ¦ Production build failed when API route imports constructed ConvexHttpClient during Next page-data collection without NEXT_PUBLIC_CONVEX_URL. | Retest Pass | npm run build passed; selected contracts and Python compile passed after fix.
REPORT-001 | Reports | Attendance Reports | As a supervisor, I can summarize attendance over a date range. | Reports fetch daily attendance for each selected date, apply a late threshold, and present daily activity plus worker-hours summaries. | src/app/reports/page.tsx; src/app/api/attendance/route.ts | Browser smoke | Tested pass | Medium | Pass | Standalone Playwright fallback found Daily Activity and no Next overlay. | Not needed yet
SCHED-001 | Schedules | Schedule Management | As an admin, I can create, edit, or delete schedules that drive attendance expectations. | Schedules page loads schedules/workers, supports day toggles, start/end times, department selection, POST/PATCH/DELETE APIs, and refreshes after changes. | src/app/schedules/page.tsx; src/app/api/schedules/route.ts; convex/schedules.ts | Browser smoke | Tested pass | High | Pass | Standalone Playwright fallback found Schedules and no Next overlay. | Not needed yet
KIOSK-001 | Kiosks | Kiosk Readiness | As an admin, I can verify device sync health and register a kiosk. | Kiosks page shows system-health readiness, status thresholds, last sync, expected worker count, last attendance upload, setup reminder, and kiosk registration form without exposing KIOSK_API_KEY. | src/app/kiosks/page.tsx; src/app/api/kiosks/route.ts; src/app/api/system-health/route.ts | test:kiosk-readiness | Tested pass | High | Pass / Pass | Kiosk readiness contract passed. ¦ Standalone Playwright fallback found Kiosk readiness and no Next overlay. | Not needed yet
ACCT-001 | Accounts | Account Management | As an admin, I can create named portal accounts and share temporary credentials safely. | Accounts page blocks non-admins, enforces password policy, generates passwords, creates Convex password users, creates portal member roles, copies credentials, and lists portal users. | src/app/accounts/page.tsx; convex/portalMembers.ts | Browser smoke; test:auth-scaffold | Retest passed | High | Retest Pass / Pass | Convex Auth scaffold contract passed after the Convex client lazy-init fix. ¦ Standalone Playwright fallback found Account Management and no Next overlay. | Not needed yet
RECOG-001 | Recognition | Recognition Calibration Lab | As a supervisor, I can review recognition quality before it corrupts attendance trust. | Recognition Lab filters attempts by date, decision, review status, confidence, and kiosk; displays summary metrics; and lets permitted users mark attempts confirmed or ignored. | src/app/calibration/recognition/page.tsx; src/components/RecognitionCalibrationLab.tsx; src/app/api/recognition-attempts/route.ts | test:recognition-attempts | Tested pass | High | Pass / Pass | Recognition attempts contract passed. ¦ Standalone Playwright fallback found Recognition and no Next overlay. | Not needed yet
BRIEF-001 | Supervisor | Shift Briefing | As a supervisor, I can preview coverage risk and first actions for a date. | Briefing fetches /api/shift-briefing, validates date, shows risk, department coverage, filtered scheduled workers, kiosk trust, review links, CSV export, and print output. | src/app/briefing/page.tsx; src/app/api/shift-briefing/route.ts; convex/shiftBriefing.ts | test:shift-briefing | Tested pass | High | Pass | PIN login returned fw-auth cookie; authenticated GET /briefing and /closeout returned 200 with expected SSR text; /exceptions returned 200 with Shift Exceptions heading; / returned 200 with Dashboard shell. | Not needed yet
EXC-001 | Supervisor | Shift Exceptions | As a supervisor, I can triage attendance exceptions created from schedule, scan sequence, kiosk, and recognition evidence. | Exceptions page filters by date/department/type/severity/status, exports CSV, supports reviewed/resolved/ignored/open statuses, links to evidence, and shows deployment-pending fallback. | src/app/exceptions/page.tsx; src/app/api/shift-exceptions/route.ts; convex/shiftExceptions.ts | test:shift-exceptions | Tested pass | High | Pass | PIN login returned fw-auth cookie; authenticated GET /briefing and /closeout returned 200 with expected SSR text; /exceptions returned 200 with Shift Exceptions heading; / returned 200 with Dashboard shell. | Not needed yet
CORR-001 | Supervisor | Attendance Corrections | As a supervisor, I can make an explicit audited correction from an exception. | Correction modal supports add clock-in, add clock-out, or void event, requires a reason, stores original attendance references when needed, and feeds effective attendance without mutating raw kiosk evidence. | src/app/exceptions/page.tsx; src/app/api/attendance-corrections/route.ts; convex/attendanceCorrections.ts; convex/attendance.ts | test:attendance-corrections | Retest passed | High | Retest Pass | Attendance corrections contract passed after the Convex client lazy-init fix. | Not needed yet
CLOSE-001 | Supervisor | Shift Closeout | As a supervisor, I can close or reopen a shift after acknowledging unresolved blockers. | Closeout fetches /api/shift-closeout, shows checklist/source links, captures supervisor name/notes/acknowledgement, blocks completion until required acknowledgement exists, saves/completes/reopens, and supports print/export. | src/app/closeout/page.tsx; src/app/api/shift-closeout/route.ts; convex/shiftCloseouts.ts | test:shift-closeout | Tested pass | High | Pass | PIN login returned fw-auth cookie; authenticated GET /briefing and /closeout returned 200 with expected SSR text; /exceptions returned 200 with Shift Exceptions heading; / returned 200 with Dashboard shell. | Not needed yet
API-001 | API | Workers API | As the app and kiosks, we can read/write worker records with safe biometric handling. | GET supports specific-worker safe prefill and admin list; include_encodings controls vector exposure; POST/PATCH/DELETE validate fields and roles. | src/app/api/workers/route.ts; convex/workers.ts | test:worker-ui; test:enrollment-permissions | Retest passed | High | Retest Pass | Production build completed after making src/lib/convex.ts lazy initialize ConvexHttpClient. ¦ Production build failed when API route imports constructed ConvexHttpClient during Next page-data collection without NEXT_PUBLIC_CONVEX_URL. | Retest Pass | npm run build passed; selected contracts and Python compile passed after fix.
API-002 | API | Attendance API | As kiosks and supervisors, we can record and read attendance events. | GET lists attendance by date/worker and uses effective attendance unless raw=true; POST records one event; bulk POST maps kiosk logs/events and preserves kiosk metadata. | src/app/api/attendance/route.ts; src/app/api/attendance/bulk/route.ts; convex/attendance.ts | test:attendance-corrections | Retest passed | High | Retest Pass | Production build completed after making src/lib/convex.ts lazy initialize ConvexHttpClient. ¦ Production build failed when API route imports constructed ConvexHttpClient during Next page-data collection without NEXT_PUBLIC_CONVEX_URL. | Retest Pass | npm run build passed; selected contracts and Python compile passed after fix.
API-003 | API | Health and Stats APIs | As supervisors and monitors, we can inspect portal health, face-service health, kiosk freshness, and day stats. | Health returns a simple status; stats returns daily counts; system-health uses raw attendance evidence, checks face service, caches briefly, and reports kiosk warnings read-only. | src/app/api/health/route.ts; src/app/api/stats/route.ts; src/app/api/system-health/route.ts; convex/stats.ts | test:worker-ui; test:attendance-corrections; test:kiosk-readiness | Retest passed | High | Retest Pass | Production build completed after making src/lib/convex.ts lazy initialize ConvexHttpClient. ¦ Production build failed when API route imports constructed ConvexHttpClient during Next page-data collection without NEXT_PUBLIC_CONVEX_URL. | Retest Pass | npm run build passed; selected contracts and Python compile passed after fix.
API-004 | API | Kiosk Sync API | As a kiosk, I can download worker encodings and update sync freshness. | /api/sync requires kiosk_id, accepts kiosk keys, updates last_sync for known kiosks, returns worker payloads changed since the provided timestamp, and does not require human auth for kiosk sync. | src/app/api/sync/route.ts; src/lib/auth.ts; pi-kiosk/sync.py | test:auth-scaffold; pi-kiosk/e2e_test.py | Retest passed | High | Retest Pass | Production build completed after making src/lib/convex.ts lazy initialize ConvexHttpClient. ¦ Production build failed when API route imports constructed ConvexHttpClient during Next page-data collection without NEXT_PUBLIC_CONVEX_URL. | Retest Pass | npm run build passed; selected contracts and Python compile passed after fix.
API-005 | API | Recognition Attempts API | As kiosks and supervisors, we can ingest and review recognition attempts. | Bulk API accepts kiosk attempts/logs/events with idempotency; read API filters by date/kiosk/decision/review/confidence; PATCH updates review status. | src/app/api/recognition-attempts/route.ts; src/app/api/recognition-attempts/bulk/route.ts; convex/recognitionAttempts.ts | test:recognition-attempts | Retest passed | High | Retest Pass / Pass | Production build completed after making src/lib/convex.ts lazy initialize ConvexHttpClient. ¦ Standalone Playwright fallback found Recognition and no Next overlay. ¦ Production build failed when API route imports constructed ConvexHttpClient during Next page-data collection without NEXT_PUBLIC_CONVEX_URL. | Retest Pass | npm run build passed; selected contracts and Python compile passed after fix.
API-006 | API | Shift Workflow APIs | As supervisor pages, we can fetch workflow data even during Convex deployment rollout. | Briefing, exceptions, closeout, and corrections validate dates/actions, enforce read/write roles, call Convex workflow functions, and return deployment-pending fallbacks for missing deployed functions where coded. | src/app/api/shift-briefing/route.ts; src/app/api/shift-exceptions/route.ts; src/app/api/shift-closeout/route.ts; src/app/api/attendance-corrections/route.ts | test:shift-briefing; test:shift-exceptions; test:shift-closeout; test:attendance-corrections | Retest passed | High | Retest Pass | Production build completed after making src/lib/convex.ts lazy initialize ConvexHttpClient. ¦ Production build failed when API route imports constructed ConvexHttpClient during Next page-data collection without NEXT_PUBLIC_CONVEX_URL. | Retest Pass | npm run build passed; selected contracts and Python compile passed after fix.
KIOSK-002 | Pi Kiosk | Recognition Clocking | As a worker, I can clock in or out at a physical kiosk with live face recognition. | Kiosk starts camera, detects largest face, checks liveness/blink where enabled, matches against local encodings, applies cooldown/last-action logic, logs accepted or rejected attempts, and shows clear status messaging. | pi-kiosk/main.py; pi-kiosk/recognition.py; pi-kiosk/liveness.py; pi-kiosk/app.py | python compile; pi-kiosk/e2e_test.py local portions | Retest passed | High | Retest Pass | All kiosk and face-service Python files compiled after the Convex client lazy-init fix. | Not needed yet
KIOSK-003 | Pi Kiosk | Offline Store and Sync | As an operator, I can trust kiosks to keep working during network interruptions. | Local SQLite stores workers, attendance, sync state, and recognition attempts; sync uploads pending attendance/attempts with idempotency keys, downloads worker updates/photos, and only marks rows synced after successful uploads. | pi-kiosk/database.py; pi-kiosk/sync.py | python compile; pi-kiosk/e2e_test.py local portions | Retest passed | High | Retest Pass | All kiosk and face-service Python files compiled after the Convex client lazy-init fix. | Not needed yet
KIOSK-004 | Pi Kiosk | Local Kiosk Web UI | As an operator at the kiosk, I can see camera/status information and perform fallback manual clock actions. | Flask UI serves index, feed/video_feed, health, status, log/today, and manual-clock endpoints; status includes kiosk identity/type and manual clock logs local attendance with a note. | pi-kiosk/app.py; pi-kiosk/templates/index.html | python compile | Retest passed | Medium | Retest Pass | All kiosk and face-service Python files compiled after the Convex client lazy-init fix. | Not needed yet
KIOSK-005 | Pi Kiosk | Setup and Diagnostics | As an implementer, I can install and diagnose a kiosk. | Setup scripts/config define server URL, kiosk identity, API key, liveness thresholds, quick camera/liveness tests, enrollment CLI, demo mode, and e2e checks. | pi-kiosk/setup.sh; pi-kiosk/config.py; pi-kiosk/quick_test.py; pi-kiosk/enroll.py; pi-kiosk/e2e_test.py; README.md | python compile; README review | Retest passed | Medium | Retest Pass | All kiosk and face-service Python files compiled after the Convex client lazy-init fix. | Not needed yet
FACE-001 | Face Service | Face Encoding and Matching | As the web app and kiosk pipeline, we can turn photos into recognition vectors and compare candidates. | FastAPI health reports model readiness; /encode rejects no-face input and returns averaged valid 512-dim encoding for photos; /match compares candidate embedding against worker encodings with threshold and score margin. | face-service/main.py; src/app/api/enroll/route.ts | python compile; pi-kiosk/e2e_test.py if service running | Retest passed | High | Retest Pass | All kiosk and face-service Python files compiled after the Convex client lazy-init fix. | Not needed yet
DOCS-001 | Operations | Setup Documentation | As an implementer, I can set up Render, Convex, kiosks, and enrollment without guessing. | README documents live dashboard, architecture, kiosk hardware/setup, env secrets, enrollment, service startup, and deployment assumptions; vision.md defines product guardrails. | README.md; vision.md; render.yaml | Static review | Tested pass | Medium | Pass | Standalone Playwright fallback found Step-by-step enrollment and no Next overlay. | Not needed yet

## Test Log
Type | ID | Story IDs | Command / Flow | Status | Details | When
Command | CMD-001 | AUTH-001,AUTH-002,AUTH-003,ACCT-001,API-004 | npm run test:auth-scaffold | Retest Pass | Convex Auth scaffold contract passed after the Convex client lazy-init fix. | 46194.8014
Command | CMD-002 | AUTH-001 | npm run test:login-error-copy | Pass | Login error copy contract passed. | 46194.7986
Command | CMD-003 | DASH-001,DASH-002,DASH-003,WORK-001,WORK-002,ENROLL-001,ENROLL-002,NAV-001,API-001,API-003 | npm run test:worker-ui | Retest Pass | Worker UI and dashboard readiness contract passed after the Convex client lazy-init fix. | 46194.8014
Command | CMD-004 | AUTH-003,ENROLL-001,ENROLL-002,WORK-002,API-001 | npm run test:enrollment-permissions | Pass | Enrollment permission contract passed. | 46194.7993
Command | CMD-005 | KIOSK-001,AUTH-003,API-003 | npm run test:kiosk-readiness | Pass | Kiosk readiness contract passed. | 46194.7993
Command | CMD-006 | RECOG-001,API-005 | npm run test:recognition-attempts | Pass | Recognition attempts contract passed. | 46194.7993
Command | CMD-007 | BRIEF-001,API-006 | npm run test:shift-briefing | Retest Pass | Shift briefing contract passed after the Convex client lazy-init fix. | 46194.8014
Command | CMD-008 | EXC-001,CORR-001,API-006,DASH-002 | npm run test:shift-exceptions | Pass | Shift exceptions contract passed. | 46194.7993
Command | CMD-009 | CLOSE-001,API-006,DASH-002 | npm run test:shift-closeout | Pass | Shift closeout contract passed. | 46194.8
Command | CMD-010 | LOG-001,CORR-001,API-002,API-003,API-006 | npm run test:attendance-corrections | Retest Pass | Attendance corrections contract passed after the Convex client lazy-init fix. | 46194.8014
Command | CMD-011 | KIOSK-002,KIOSK-003,KIOSK-004,KIOSK-005,FACE-001 | python3 -m py_compile $(find pi-kiosk face-service -name '*.py' -print) | Retest Pass | All kiosk and face-service Python files compiled after the Convex client lazy-init fix. | 46194.8014
Command | CMD-012 | API-001,API-002,API-003,API-004,API-005,API-006,DASH-001,DASH-002,LOG-001 | npm run build | Fail | Initial build failed during page-data collection for /api/attendance: ConvexHttpClient was created with undefined deployment address. | 46194.8
Command | CMD-013 | API-001,API-002,API-003,API-004,API-005,API-006,DASH-001,DASH-002,LOG-001 | npm run build | Retest Pass | Production build completed after making src/lib/convex.ts lazy initialize ConvexHttpClient. | 46194.8007
Command | CMD-014 | BRIEF-001,EXC-001,CLOSE-001,DASH-001,AUTH-001 | curl cookie-jar protected route probe | Pass | PIN login returned fw-auth cookie; authenticated GET /briefing and /closeout returned 200 with expected SSR text; /exceptions returned 200 with Shift Exceptions heading; / returned 200 with Dashboard shell. | 46194.8187
Browser | BROWSER-LOGIN | AUTH-001,DASH-001,DASH-002,NAV-001 | /login -> PIN fallback -> / dashboard | Pass | Standalone Playwright fallback: PIN fallback enabled after input and navigated to dashboard with Action Center visible. | 46194.8096
Browser | BROWSER-WORKERS | WORK-001,WORK-002 | /workers renders expected surface | Pass | Standalone Playwright fallback found Workers and no Next overlay. | 46194.8099
Browser | BROWSER-ENROLL | ENROLL-001,ENROLL-002 | /enroll renders expected surface | Pass | Standalone Playwright fallback found Enroll and no Next overlay. | 46194.8104
Browser | BROWSER-ONBOARDING | ONBOARD-001,DOCS-001 | /onboarding renders expected surface | Pass | Standalone Playwright fallback found Step-by-step enrollment and no Next overlay. | 46194.8105
Browser | BROWSER-LOG | LOG-001 | /log renders expected surface | Pass | Standalone Playwright fallback found Correction history and no Next overlay. | 46194.8108
Browser | BROWSER-REPORTS | REPORT-001 | /reports renders expected surface | Pass | Standalone Playwright fallback found Daily Activity and no Next overlay. | 46194.8113
Browser | BROWSER-SCHEDULES | SCHED-001 | /schedules renders expected surface | Pass | Standalone Playwright fallback found Schedules and no Next overlay. | 46194.8114
Browser | BROWSER-KIOSKS | KIOSK-001 | /kiosks renders expected surface | Pass | Standalone Playwright fallback found Kiosk readiness and no Next overlay. | 46194.8115
Browser | BROWSER-ACCOUNTS | ACCT-001 | /accounts renders expected surface | Pass | Standalone Playwright fallback found Account Management and no Next overlay. | 46194.8115
Browser | BROWSER-CALIBRATION-RECOGNITION | RECOG-001,API-005 | /calibration/recognition renders expected surface | Pass | Standalone Playwright fallback found Recognition and no Next overlay. | 46194.8117
Browser | BROWSER-IAB-BLOCKER | AUTH-001 | In-app Browser PIN input interaction | Blocked | In-app Browser rendered /login but repeated locator interaction flipped the dev page into a Next overlay: TypeError Cannot read properties of undefined reading call. Standalone Playwright did not reproduce the login failure. | 46194.8056

## Fix Log
Fix ID | Story IDs | Issue | Status | Files | Retest | When
FIX-001 | API-001,API-002,API-003,API-004,API-005,API-006,DASH-001,DASH-002,LOG-001 | Production build failed when API route imports constructed ConvexHttpClient during Next page-data collection without NEXT_PUBLIC_CONVEX_URL. | Retest Pass | src/lib/convex.ts | npm run build passed; selected contracts and Python compile passed after fix. | 46194.8014